## Gantt Chart
Tasks | Project Plan - Weeks (5 business day per week) - s2850345, s5301986, s5251549
| 1 31/07 - 04/08 | 2 7/08 - 11/08 | 3 14/08 - 18/08 | 4 21/08 - 25/08 | 5 28/08 - 01/09 | 6 04/09 - 08/09 | 7 11/09 - 15/09 | 8 18/09 - 22/09 | 9 25/09 - 29/09 | 10 02/10 - 06/10
Initiating
1.1 Setup Git Repository
1.2 Define communication strategies and tools
1.3 Decide on dataset to be used
1.4 Clone templates
1.5 Define project objectives
1.6 Identify team members skills
1.7 Assign roles and responsibilities
1.8 Familiarize with Victoria State Dataset
1.9 Identify primary data categories
Planning
2.0 Set milestones and deadlines
2.1 Develop project plan document
2.2 Create Gantt chart and estimate times
2.3 Develop system vision statement
2.4 Requirements
2.5 Software design diagram
2.6 Software component functions/Data
2.7 Algorithm Pseudocode
2.8 User interface design
Executing
3.0 Data extraction
3.1 Design main dashboard interface
3.2 Design data visualization components
3.3 Design data input and filtering components
3.4 Implement user-selected time period feature
3.5 Implement keyword-based accident retrieval
3.6 Implement Alcohol impact analysis
3.7 Research and implement another analysis tool
Controlling
4.0 Regular git updates
4.1 Check alignment with assignment rubric often
4.2 Beta test software with selected user group
4.3 Collect and document user feedback
4.4 Address bugs and issues identified during testing
4.5 Implement feature requests and improvements
Closing
5.0 Ensure all performance standards are achieved
5.1 Collect feedback and get approval from team
5.2 Present the final software
5.3 Finalize and provide project documentation
5.4 Document lessons learned